## Progress Report
Project 10: Mesmer Low Flow Diversion Project | Project Description:
Implementing Agency: Los Angeles County Public Works
BUDGET CATEGORIES | Percent | Work Accomplished During this Reporting Period | Work Progress Per Schedule | Work Anticipated for the Next Reporting Period | Photos
Budget Category (a): Direct Project Administration
Task 1 Project Management
Task 2 Reporting
Budget Category (b) Land Purchase/Easement
Task 3 Land Purchase (Not Applicable) | Not Applicable
Budget Category (c) Planning/ Design/ Engineering andEnvironmental Documentation
Task 4 Feasibility Studies
Task 5 CEQA Documentation
Task 6 Permitting
Task 7 Design
Task 8 Project Monitoring Plan
Budget Category (d) Construction/Implementation Activities
Task 9 Contract Services
Task 10 Implementation Administration
Task 11 Implementation
Subtask 11(a) Equipment Procurement
Subtask 11(b) Customer Outreach
Subtask 11(c) Software Setup and Implementation
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provide the percent completion for the task. The starting percentage should coincide with the percentage included in your work plan submitted as part of the proposal. If no work was completed during the reporting period, the percent should remain the same as the previous report.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include milestones, deliverable(s) completed and submitted, and meetings held or attended during the reporting period. For deliverables, make sure to reference the same names list in Work Plan.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicate if work progress is "Ahead of Schedule", "On Schedule", or "Behind Schedule". If Behind Schedule, reason for delay must be provided.
Note on F3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If photos are included, indicate if the photos are "PRE-Construction", "ACTIVE (during) Construction", or "POST Construction". Leave blank, if no photos are included for the reporting period.

## Personnel Hours - TABLE
City of Culver City - Personnel Hours Summary
Project 10: | Mesmer Low Flow Diversion Project
Date:
Invoicing Period:
Budget Category A: Direct Project Administration
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
|  |  |  | Total | 0
Budget Category B: Land Purchase/Easements
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
0
|  |  |  | Total | 0
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | Provide preliminary comments on design | 80 | 60 | 4800
Karen Taylor | Project Engineer II | Final design review | 20 | 100 | 2000
0
|  |  |  | Total | 6800
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | On site Engineering | 120 | 60 | 7200
0
|  |  |  | Total | 7200

## Backup Doc Summary TABLE
Backup Documentation Summary Table |  |  |  | Invoice #:
Grantee: | Los Angeles County Flood Control District |  |  | Date of Invoice:
Invoicing Period:
Project 10: | Mesmer Low Flow Diversion Project
Project Proponent: | City of Culver City
Invoice Description | Notes | Invoice # | Invoice Date | Invoice Amount | Invoice Packet Page #
Budget Category (A) Direct Project Management
Subtotal (A) |  |  |  | 0
Budget Category (B): Land Purchase/Easement
Subtotal (B) |  |  |  | 0
Budget Category (C): Planning/Design/Engineering/Environmental Documentation
Subtotal (C) |  |  |  | 0
|  |  | GRAND TOTAL | 0

## Cash Projections
Cash Projections |  | Invoice #:
Grantee: | Los Angeles County Flood Control District
Invoicing Period:
Project 10: | Mesmer Low Flow Diversion Project
Project Proponent: | City of Culver City
Project Cash Projection for next six months:
Month |  |  | TOTAL
Amount
TOTAL

## Cover Letter SAMPLE
2021-10-31
Amanda Guzman-Perez
Los Angeles County Flood Control District
Department of Public Works
900 S Fremont Avenue
Alhambra, CA 91803
SUBJECT: | Proposition 1 Round 1 - Progress Report & Invoice #1
Invoicing Period: July 1, 2021 to September 30, 2021
Project 1 - Mesmer Los Flow Diversion Project
City of Culver City
Dear Ms. Guzman-Perez:
Enclosed is the July 1 to September 30, 2020 quarterly Progress Report and Invoice for the Mesmer
Low Flow Diversion Project, which is currently in pre-construction phase and is funded through the
Proposition 1 Round 1 Grant Agreement 4600013903. The progress report provides the project status
from July 1 to September 30, 2020 schedule information and anticipated activities for the next
quarter.
I hereby verify that I am authorized signatory for the City of Culver City and as such I can sign and bind the
City of Culver City as it relates to the above-mentioned project. I certify that this progress report and invoice
documentation in all respects true, correct, supportable by available backup documentation, and in compliance
with all terms/conditions, laws, and regulations governing its payment.
If you have any questions, please contact Joe Smith at (555) 555-5555 or jsmith@city.gov or John Doe at
(555) 555-5556 or jdoe@city.gov.
Cordially,

## Personnel Hours - SAMPLE
City of Culver City - Personnel Hours Summary - SAMPLE
Project 10: | Mesmer Low Flow Diversion Project
Date: | 2021-10-31
Invoicing Period: | 7/1/2021 - 9/30/2021
Budget Category A: Direct Project Administration
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Susie Adams | Accountant II | Invoice preparation | 5 | 40 | 200
Matt Brown | Staff Engineer I | Coordination with project proponents, set up kick-off meetings | 8 | 50 | 400
Matt Brown | Staff Engineer II | Quarterly Report preparation and coordination with project proponents | 15 | 60 | 900
Karen Taylor | Project Engineer II | Working with DWR to get City of Example under agreement, attended design meetings, coordination meetings with consultants, internal project management meetings with Director of Public Works | 43 | 100 | 4300
|  |  |  | Total | 5800
Budget Category B: Land Purchase/Easements
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Michelle Kwong | Land Agent I | Verify easements, contact land owners | 40 | 90 | 3600
0
0
|  |  |  | Total | 3600
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | Provide preliminary comments on design | 80 | 60 | 4800
Karen Taylor | Project Engineer II | Final design review | 20 | 100 | 2000
0
|  |  |  | Total | 6800
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | On site Engineering | 120 | 60 | 7200
0
|  |  |  | Total | 7200

## Backup Doc Summary SAMPLE
Backup Documentation Summary Table - SAMPLE |  |  |  | Invoice #: | 1
Grantee: | Los Angeles Control Flood Control District |  |  | Date of Invoice: | 2021-10-31
Invoicing Period: | 7/1/2021 - 9/30/2021
Project 2: | Mesmer Low Flow Diversion Project
Project Proponent: | City of Culver City
Invoice Description | Notes | Invoice # | Invoice Date | Invoice Amount | Invoice Packet Page #
Budget Category (A) Direct Project Management
Engineering Consultant, Inc. |  | 143383 | 2021-07-22 | 11252.79 | 7
Subtotal (A) |  |  |  | 11252.79
Budget Category (C): Planning/Design/Engineering/Environmental Documentation
Engineering Consultant, Inc. | Pipeline Design | 143383 | 2021-07-22 | 4724.69 | 1
Subtotal (C) |  |  |  | 4724.69
Budget Category (D): Construction/Implementation
Engineering Consultant, Inc. | Pipeline Bid Period Support | 143383 | 2021-07-22 | 8575.12
Project Consultant, Inc | Site Evaluation and Soil Testing | 2 | 2021-09-20 | 381600.8 | 5
Subtotal (D) |  |  |  | 390175.92
|  |  | GRAND TOTAL | 406153.4

## Cash Projections SAMPLE
Cash Projections - SAMPLE |  |  |  | Invoice #: | 1
Grantee: | Los Angeles County Flood Control District
Invoicing Period: | 7/1/2021 - 9/30/2021
Project 10: | Mesmer Low Flow Diversion Project
Project Proponent: | City of Culver City
Project Cash Projection for next six months: October 2021 through March 2022
Month | Oct | Nov | Dec | Jan | Feb | March | TOTAL
Amount | 45000 | 30000 | 35000 | 20000 | 10000 | 40000 | 180000
TOTAL | 45000 | 30000 | 35000 | 20000 | 10000 | 40000 | 180000