## Progress Report
PROGRESS REPORT NUMBER & REPORTING PERIOD: | [5 empty] | Progress Report 1 - January 1, 2015 to September 30, 2021
Project 2: East Los Angeles Sustainable Median Stormwater Capture Project | Project Description: | East Los Angeles Sustainable Median Stormwater Capture Project involves the installation of stormwater and urban runoff diversion systems with pretreatment units connecting to over 100 infiltration dry-wells located within existing roadway medians. The system and drywells will divert and infiltrate up to 22 acre-ft per event of the stormwater, and urban runoff into the existing Central Basin Groundwater Aquifer for ultimate reuse, thereby reducing the need for imported water. This system is expected to improve water quality in the region by reducing the amount of pollutants entering local rivers and waterways. Over 300 trees and 273,400 square feet of landscaping will be installed, which will assist in addressing climate change by reducing heat island effect. Landscaping will include drought tolerant planting with a drip irrigation system to establish the plants and ensure conservation of water. |  |  |  | Progress Report 2 - October 1, 2021 to December 31, 2021
Implementing Agency: Los Angeles County Public Works | [5 empty] | Progress Report 3 - January 1, 2022 to March 31, 2022
BUDGET CATEGORIES | Percent | Work Accomplished During this Reporting Period | Work Progress Per Schedule | Work Anticipated for the Next Reporting Period | Photos | Progress Report 4 - April 1, 2022 to June 30, 2022
Budget Category (a): Direct Project Administration | [5 empty] | Progress Report 5 - July 1, 2022 to September 30, 2022
Task 1 Project Management | [5 empty] | Progress Report 6 - October 1, 2022 to December 31, 2022
Task 2 Reporting | [5 empty] | Progress Report 7 - January 1, 2023 to March 31, 2023
Budget Category (b) Land Purchase/Easement | [5 empty] | Progress Report 8 - April 1, 2023 to June 30, 2023
Task 3 Land Purchase (Not Applicable) | [5 empty] | Progress Report 9 - July 1, 2023 to September 30, 2023
Budget Category (c) Planning/ Design/ Engineering andEnvironmental Documentation | [5 empty] | Progress Report 10 - October 1, 2023 to December 31, 2023
Task 4 Feasibility Studies | [5 empty] | Progress Report 11 - January 1, 2024 to March 31, 2024
Task 5 CEQA Documentation
Task 6 Permitting
Task 7 Design
Task 8 Project Monitoring Plan
Budget Category (d) Construction/Implementation Activities
Task 9 Contract Services
Task 10 Construction Administration
Task 11 Construction
Subtask 11(a) Mobilization and Demobilization
Subtask 11(b) Site Preparation
Subtask 11(c) Install, construct, excavate
Subtask 11(d) Improve the site per design or restore to pre-existing conditions
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provide the percent completion for the task. If no work was completed during the reporting period, the percent should remain the same as the previous report.
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include milestones, deliverable(s) completed and submitted, and meetings held or attended during the reporting period. For deliverables, make sure to reference the same names list in Work Plan.
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicate if work progress is "Ahead of Schedule", "On Schedule", or "Behind Schedule". If Behind Schedule, reason for delay must be provided.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If photos are included, indicate if the photos are "PRE-Construction", "ACTIVE (during) Construction", or "POST Construction". Leave blank, if no photos are included for the reporting period.

## Personnel Hours - TABLE
January 1, 2015 to September 30, 2021
Los Angeles County Public Works - Personnel Hours Summary | [5 empty] | October 1, 2021 to December 31, 2021
Project 2: | East Los Angeles Sustainable Median Stormwater Capture Project |  |  |  |  | January 1, 2022 to March 31, 2022
April 1, 2022 to June 30, 2022
Date: | [5 empty] | July 1, 2022 to September 30, 2022
Invoicing Period: | [5 empty] | October 1, 2022 to December 31, 2022
January 1, 2023 to March 31, 2023
Budget Category A: Direct Project Administration | [5 empty] | April 1, 2023 to June 30, 2023
July 1, 2023 to September 30, 2023
Employee | Classification | Work Performed | Hours | Hourly Rate | Total | October 1, 2023 to December 31, 2023
January 1, 2024 to March 31, 2024
|  |  |  | Total | 0
Budget Category B: Land Purchase/Easements
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
0
|  |  |  | Total | 0
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | Provide preliminary comments on design | 80 | 60 | 4800
Karen Taylor | Project Engineer II | Final design review | 20 | 100 | 2000
0
|  |  |  | Total | 6800
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | On site Engineering | 120 | 60 | 7200
0
|  |  |  | Total | 7200
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
|  |  |  | Total | 0
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
0
|  |  |  | Total | 0

## Backup Doc Summary TABLE
Backup Documentation Summary Table |  |  |  | Invoice #: |  | January 1, 2015 to September 30, 2021
October 1, 2021 to December 31, 2021
Grantee: | Los Angeles County Flood Control District |  |  | Date of Invoice: |  | January 1, 2022 to March 31, 2022
Invoicing Period: | [5 empty] | April 1, 2022 to June 30, 2022
July 1, 2022 to September 30, 2022
Project 2: | East Los Angeles Sustainable Median Stormwater Capture Project |  |  |  |  | October 1, 2022 to December 31, 2022
Project Proponent: | Los Angeles County Public Works |  |  |  |  | January 1, 2023 to March 31, 2023
April 1, 2023 to June 30, 2023
Invoice Description | Notes | Invoice # | Invoice Date | Invoice Amount | Invoice Packet Page # | July 1, 2023 to September 30, 2023
Budget Category (A) Direct Project Management | [5 empty] | October 1, 2023 to December 31, 2023
January 1, 2024 to March 31, 2024
Subtotal (A) |  |  |  | 0
Budget Category (B): Land Purchase/Easement
Subtotal (B) |  |  |  | 0
Budget Category (C): Planning/Design/Engineering/Environmental Documentation
Subtotal (C) |  |  |  | 0
Budget Category (D): Construction/Implementation
Subtotal (D) |  |  |  | 0
|  |  | GRAND TOTAL | 0

## Cash Projections
Cash Projections |  | Invoice #: |  | January 1, 2015 to September 30, 2021
October 1, 2021 to December 31, 2021
Grantee: | Los Angeles County Flood Control District |  |  | January 1, 2022 to March 31, 2022
Invoicing Period: |  |  |  | April 1, 2022 to June 30, 2022
July 1, 2022 to September 30, 2022
Project 2: | East Los Angeles Sustainable Median Stormwater Capture Project |  |  | October 1, 2022 to December 31, 2022
Project Proponent: | Los Angeles County Public Works |  |  | January 1, 2023 to March 31, 2023
April 1, 2023 to June 30, 2023
Project Cash Projection for next six months: |  |  |  | July 1, 2023 to September 30, 2023
Month |  |  | TOTAL | October 1, 2023 to December 31, 2023
Amount
TOTAL

## Cover Letter SAMPLE
2021-10-31
Amanda Guzman-Perez
Los Angeles County Flood Control District
Department of Public Works
900 S Fremont Avenue
Alhambra, CA 91803
SUBJECT: | Proposition 1 Round 1 - Progress Report & Invoice #1
Invoicing Period: July 1, 2021 to September 30, 2021
Project 2 - East Los Angeles Sustainable Median Stormwater Capture Project
Los Angeles County Public Works
Dear Ms. Guzman-Perez:
Enclosed is the July 1 to September 30, 2020 quarterly Progress Report and Invoice for the East Los Angeles
Sustainable Median Stormwater Capture Project, which is currently in pre-construction phase and is funded through
the Proposition 1 Round 1 Grant Agreement 4600013903. The progress report provides the project status
from July 1 to September 30, 2020 schedule information and anticipated activities for the next quarter.
I hereby verify that I am authorized signatory for the Los Angeles County Public Works and as such I can sign and
bind the Los Angeles County Public Works as it relates to the above-mentioned project. I certify that this
progress report and invoice documentation in all respects true, correct, supportable by available backup documentation,
and in compliance will all terms/conditions, laws, and regulations governing its payment.
If you have any questions, please contact Joe Smith at (555) 555-5555 or jsmith@dpw.lacounty.gov or John Doe at
(555) 555-5556 or jdoe@dpw.lacounty.gov
Cordially,

## Personnel Hours - SAMPLE
Los Angeles County Public Works - Personnel Hours Summary - SAMPLE
Project 2: | East Los Angeles Sustainable Median Stormwater Capture Project
Date: | 2021-10-31
Invoicing Period: | 7/1/2021 - 9/30/2021
Budget Category A: Direct Project Administration
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
|  |  |  | Total | 0
Budget Category B: Land Purchase/Easements
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
0
0
|  |  |  | Total | 0
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | Provide preliminary comments on design | 80 | 60 | 4800
Karen Taylor | Project Engineer II | Final design review | 20 | 100 | 2000
0
|  |  |  | Total | 6800
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | On site Engineering | 120 | 60 | 7200
0
|  |  |  | Total | 7200
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
John Smith | Engineer | Finalized CEQA and permits | 2 | 100 | 200
0
0
|  |  |  | Total | 200
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
John Smith | Engineer | Hire contractor for construction phase. | 10 | 100 | 1000
0
0
|  |  |  | Total | 1000

## Backup Doc Summary SAMPLE
Backup Documentation Summary Table - SAMPLE |  |  |  | Invoice #: | 1
Grantee: | Los Angeles Control Flood Control District |  |  | Date of Invoice: | 2021-10-31
Invoicing Period: | 7/1/2021 - 9/30/2021
Project 2: | East Los Angeles Sustainable Median Stormwater Capture Project
Project Proponent: | Los Angeles County Public Works
Invoice Description | Notes | Invoice # | Invoice Date | Invoice Amount | Invoice Packet Page #
Budget Category (A) Direct Project Management
Subtotal (A) |  |  |  | 0
Budget Category (C): Planning/Design/Engineering/Environmental Documentation
Los Angeles County Public Works | See Personnel Table | Table | 2021-09-30 | 200 | 1
Subtotal (C) |  |  |  | 200
Budget Category (D): Construction/Implementation
Los Angeles County Public Works | See Personnel Table | Table | 2021-09-30 | 200 | 5
Subtotal (D) |  |  |  | 200
|  |  | GRAND TOTAL | 400

## Cash Projections SAMPLE
Cash Projections - SAMPLE |  |  |  | Invoice #: | 1
Grantee: | Los Angeles County Flood Control District
Invoicing Period: | 7/1/2021 - 9/30/2021
Project 2: | East Los Angeles Sustainable Median Stormwater Capture Project
Project Proponent: | Los Angeles County Public Works
Project Cash Projection for next six months: October 2021 through March 2022
Month | Oct | Nov | Dec | Jan | Feb | March | TOTAL
Amount | 45000 | 30000 | 35000 | 20000 | 10000 | 40000 | 180000
TOTAL | 45000 | 30000 | 35000 | 20000 | 10000 | 40000 | 180000