## Progress Report
PROGRESS REPORT NUMBER & REPORTING PERIOD: | [5 empty] | Progress Report 1 - January 1, 2015 to September 30, 2021
Project 5: Advanced Metering Infrastructure Project | Project Description: | Advanced Metering Infrastructure Project (District 29) includes installation of Advanced Metering Infrastructure (AMI) technology for 7,233 connections in District No. 29, Malibu. The AMI project will serve customers in Malibu as well as the surrounding unincorporated communities in Topanga. The District will convert existing residential, commercial, and industrial water meters to AMI smart meters with advanced metering capabilities. Additionally, the District will install data collection devices and host server software that will integrate with utility software applications to analyze meter data in real time, which will enhance customer service by empowering customers with tools to monitor water usage, identify leaks, and maximize water use efficiency. The District estimates this project will conserve approximately 1,099 acre-feet of water per year. AMI will also reduce carbon dioxide emissions by approximately 3,539 US tons of carbon dioxide per year. |  |  |  | Progress Report 2 - October 1, 2021 to December 31, 2021
Implementing Agency: Los Angeles County Waterworks District 29 - Malibu | [5 empty] | Progress Report 3 - January 1, 2022 to March 31, 2022
BUDGET CATEGORIES | Percent | Work Accomplished During this Reporting Period | Work Progress Per Schedule | Work Anticipated for the Next Reporting Period | Photos | Progress Report 4 - April 1, 2022 to June 30, 2022
Budget Category (a): Direct Project Administration | [5 empty] | Progress Report 5 - July 1, 2022 to September 30, 2022
Task 1 Project Management | [5 empty] | Progress Report 6 - October 1, 2022 to December 31, 2022
Task 2 Reporting | [5 empty] | Progress Report 7 - January 1, 2023 to March 31, 2023
Budget Category (b) Land Purchase/Easement | [5 empty] | Progress Report 8 - April 1, 2023 to June 30, 2023
Task 3 Land Purchase (Not Applicable) | [5 empty] | Progress Report 9 - July 1, 2023 to September 30, 2023
Budget Category (c) Planning/ Design/ Engineering andEnvironmental Documentation | [5 empty] | Progress Report 10 - October 1, 2023 to December 31, 2023
Task 4 Feasibility Studies | [5 empty] | Progress Report 11 - January 1, 2024 to March 31, 2024
Task 5 CEQA Documentation
Task 6 Permitting (Not Applicable)
Task 7 Design
Task 8 Project Monitoring Plan
Budget Category (d) Construction/Implementation Activities
Task 9 Contract Services
Task 10 Construction Administration
Task 11 Construction
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provide the percent completion for the task. If no work was completed during the reporting period, the percent should remain the same as the previous report.
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include milestones, deliverable(s) completed and submitted, and meetings held or attended during the reporting period. For deliverables, make sure to reference the same names list in Work Plan.
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicate if work progress is "Ahead of Schedule", "On Schedule", or "Behind Schedule". If Behind Schedule, reason for delay must be provided.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If photos are included, indicate if the photos are "PRE-Construction", "ACTIVE (during) Construction", or "POST Construction". Leave blank, if no photos are included for the reporting period.

## Personnel Hours - TABLE
January 1, 2015 to September 30, 2021
Los Angeles County Waterworks District 29 Malibu - Personnel Hours Summary | [5 empty] | October 1, 2021 to December 31, 2021
Project 5: | Advanced Metering Infrastructure Project |  |  |  |  | January 1, 2022 to March 31, 2022
April 1, 2022 to June 30, 2022
Date: | [5 empty] | July 1, 2022 to September 30, 2022
Invoicing Period: | [5 empty] | October 1, 2022 to December 31, 2022
January 1, 2023 to March 31, 2023
Budget Category A: Direct Project Administration | [5 empty] | April 1, 2023 to June 30, 2023
July 1, 2023 to September 30, 2023
Employee | Classification | Work Performed | Hours | Hourly Rate | Total | October 1, 2023 to December 31, 2023
January 1, 2024 to March 31, 2024
|  |  |  | Total | 0
Budget Category B: Land Purchase/Easements
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
0
|  |  |  | Total | 0
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | Provide preliminary comments on design | 80 | 60 | 4800
Karen Taylor | Project Engineer II | Final design review | 20 | 100 | 2000
0
|  |  |  | Total | 6800
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | On site Engineering | 120 | 60 | 7200
0
|  |  |  | Total | 7200
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
|  |  |  | Total | 0
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
0
|  |  |  | Total | 0

## Backup Doc Summary TABLE
Backup Documentation Summary Table |  |  |  | Invoice #: |  | January 1, 2015 to September 30, 2021
October 1, 2021 to December 31, 2021
Grantee: | Los Angeles County Flood Control District |  |  | Date of Invoice: |  | January 1, 2022 to March 31, 2022
Invoicing Period: | [5 empty] | April 1, 2022 to June 30, 2022
July 1, 2022 to September 30, 2022
Project 5: | Advanced Metering Infrastructure Project |  |  |  |  | October 1, 2022 to December 31, 2022
Project Proponent: | Los Angeles County Waterworks District 29 - Malibu |  |  |  |  | January 1, 2023 to March 31, 2023
April 1, 2023 to June 30, 2023
Invoice Description | Notes | Invoice # | Invoice Date | Invoice Amount | Invoice Packet Page # | July 1, 2023 to September 30, 2023
Budget Category (A) Direct Project Management | [5 empty] | October 1, 2023 to December 31, 2023
January 1, 2024 to March 31, 2024
Subtotal (A) |  |  |  | 0
Budget Category (B): Land Purchase/Easement
Subtotal (B) |  |  |  | 0
Budget Category (C): Planning/Design/Engineering/Environmental Documentation
Subtotal (C) |  |  |  | 0
Budget Category (D): Construction/Implementation
Subtotal (D) |  |  |  | 0
|  |  | GRAND TOTAL | 0

## Cash Projections
Cash Projections |  | Invoice #: |  | January 1, 2015 to September 30, 2021
October 1, 2021 to December 31, 2021
Grantee: | Los Angeles County Flood Control District |  |  | January 1, 2022 to March 31, 2022
Invoicing Period: |  |  |  | April 1, 2022 to June 30, 2022
July 1, 2022 to September 30, 2022
Project 5: | Advanced Metering Infrastructure Project |  |  | October 1, 2022 to December 31, 2022
Project Proponent: | Los Angeles County Waterworks District 29 - Malibu |  |  | January 1, 2023 to March 31, 2023
April 1, 2023 to June 30, 2023
Project Cash Projection for next six months: |  |  |  | July 1, 2023 to September 30, 2023
Month |  |  | TOTAL | October 1, 2023 to December 31, 2023
Amount
TOTAL

## Cover Letter SAMPLE
2021-10-31
Amanda Guzman-Perez
Los Angeles County Flood Control District
Department of Public Works
900 S Fremont Avenue
Alhambra, CA 91803
SUBJECT: | Proposition 1 Round 1 - Progress Report & Invoice #1
Invoicing Period: July 1, 2021 to September 30, 2021
Project 5 - Advanced Metering Infrastructure Project
Los Angeles County Waterworks District 29 - Malibu
Dear Ms. Guzman-Perez:
Enclosed is the July 1 to September 30, 2020 quarterly Progress Report and Invoice for the Advanced
Metering Infrastructure Project, which is currently in pre-construction phase and is funded through
the Proposition 1 Round 1 Grant Agreement 4600013903. The progress report provides the project status
from July 1 to September 30, 2020 schedule information and anticipated activities for the next quarter.
I hereby verify that I am authorized signatory for the Los Angeles County Waterworks District 29 - Malibu and
as such can sign and bind the Los Angeles County Public Waterworks District 29 - Malibu as it relates to the above-
mentioned project. I certify that this progress report and invoice documentation in all respects true, correct,
supportable by available backup documentation, and in compliance will all terms/conditions, laws, and regulations
governing its payment.
If you have any questions, please contact Joe Smith at (555) 555-5555 or jsmith@dpw.lacounty.gov or John Doe at
(555) 555-5556 or jdoe@dpw.lacounty.gov
Cordially,

## Personnel Hours - SAMPLE
Los Angeles County Waterworks District 29 Malibu - Personnel Hours Summary - SAMPLE
Project 5: | Advanced Metering Infrastructure Project
Date: | 2021-10-31
Invoicing Period: | 7/1/2021 - 9/30/2021
Budget Category A: Direct Project Administration
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
|  |  |  | Total | 0
Budget Category B: Land Purchase/Easements
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
0
0
|  |  |  | Total | 0
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | Provide preliminary comments on design | 80 | 60 | 4800
Karen Taylor | Project Engineer II | Final design review | 20 | 100 | 2000
0
|  |  |  | Total | 6800
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
Matt Brown | Staff Engineer II | On site Engineering | 120 | 60 | 7200
0
|  |  |  | Total | 7200
Budget Category C: Planning/Design/Engineering/Environmental Documentation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
John Smith | Engineer | Finalized CEQA and permits | 2 | 100 | 200
0
0
|  |  |  | Total | 200
Budget Category D: Construction/Implementation
Employee | Classification | Work Performed | Hours | Hourly Rate | Total
John Smith | Engineer | Hire contractor for construction phase. | 10 | 100 | 1000
0
0
|  |  |  | Total | 1000

## Backup Doc Summary SAMPLE
Backup Documentation Summary Table - SAMPLE |  |  |  | Invoice #: | 1
Grantee: | Los Angeles Control Flood Control District |  |  | Date of Invoice: | 2021-10-31
Invoicing Period: | 7/1/2021 - 9/30/2021
Project 5: | Advanced Metering Infrastructure Project
Project Proponent: | Los Angeles County Waterworks District 29 - Malibu
Invoice Description | Notes | Invoice # | Invoice Date | Invoice Amount | Invoice Packet Page #
Budget Category (A) Direct Project Management
Subtotal (A) |  |  |  | 0
Budget Category (C): Planning/Design/Engineering/Environmental Documentation
Los Angeles County Waterworks District 29 - Malibu | See Personnel Table | Table | 2021-09-30 | 200 | 1
Subtotal (C) |  |  |  | 200
Budget Category (D): Construction/Implementation
Los Angeles County Waterworks District 29 - Malibu | See Personnel Table | Table | 2021-09-30 | 200 | 5
Subtotal (D) |  |  |  | 200
|  |  | GRAND TOTAL | 400

## Cash Projections SAMPLE
Cash Projections - SAMPLE |  |  |  | Invoice #: | 1
Grantee: | Los Angeles County Flood Control District
Invoicing Period: | 7/1/2021 - 9/30/2021
Project 5: | Advanced Metering Infrastructure Project
Project Proponent: | Los Angeles County Waterworks District 29 - Malibu
Project Cash Projection for next six months: October 2021 through March 2022
Month | Oct | Nov | Dec | Jan | Feb | March | TOTAL
Amount | 45000 | 30000 | 35000 | 20000 | 10000 | 40000 | 180000
TOTAL | 45000 | 30000 | 35000 | 20000 | 10000 | 40000 | 180000